## Slide 1: Syria CALL Evaluation Synthesis and Gap Analysis (ESGA) Findings and Conclusions
UNEG EPE panel discussion, WIPO Geneva– 25th April 2016
James Darcy

## Slide 2: ESGA purpose, scope, methodology
Purpose: to provide an overview of results of learning and accountability efforts undertaken thus far => indication of the evolution of the humanitarian response, its challenges and achievements. Plus identification of areas for further inquiry.
Scope: Syria and refugee responses: focus on ethnic Syrian refugees (not e.g. situation of Kurds, Palestinians, Yazedi, Turkmen). Iraq and Egypt not included; little coverage of Turkey. Refugee responses in Europe not covered.
Methodology: Based on review of 24 publicly available evaluative studies. ‘Editorial narrative’ approach, based on judgment about significance and analysis of evidence strength.

## Slide 3: The reference material
Region-wide scope
(i) Multi-agency: IASC OPR, Danida (DHA strategy), AusAID, DEC
(ii) Single agency: WFP, UNHCR RTE, UNICEF, OCHA, IFRC, HelpAge
Country /programme specific
UNHCR (Lebanon + Jordan)
Oxfam x 2 (Lebanon, Jordan), Support to Life (Turkey)
NRC (Lebanon - shelter), IRC [Lebanon- cash assistance]
Caritas (Jordan)
UNICEF x 3 – Turkey; Jordan x 2 (Educ, PSS)(multi-stakeholder)
Thematic reviews/studies
SNAP (Mid-term review of assessment project), REACH (Review of impact of UNSC Resolutions), Danish MFA (Protection meta-analysis), ICVA (Review of Pooled Funds)
Notes: Variable perspectives – but mostly single-agency

## Slide 4: ESGA methodology
Not a meta-analysis, but a compilation of key findings under seven ‘thematic clusters’ based on identified themes.
Looking for patterns and recurrent or contrasting findings, to compile an ‘editorial narrative’ asking : What does the available evidence tell us about specific topics and the response overall?
Some weighting of material according to evidence strength (see matrix). Content of both synthesis & gap analysis influenced by this.
Decisions about inclusion of material in synthesis based mainly on judgment of author about relevance and apparent significance of findings. Identification of gaps based on (i) what might be expected from evaluations of comparable responses, (ii) the experience and judgment of the author.

## Slide 5
Red = full evaluation, field based, in-depth Green = lighter review, RTE or desk-based | 1. HCR RTE | 2. IASC OPR | 3. HCR L/J | 4. WFP Reg | 5. UNICEF Reg | 6. OCHA Reg
Date | Jul-13 | Jul-15 | Jan-15 | Apr-15 | Jan-16 | Aug-15
Period covered | Spring 2013 | Spring 2015 | Jan 13 to April 14 | 2011 to end 2014 | 2012 to end 2015 | 2011 - mid2015
Theme |  |  |  |  |  | 
Political space for international aid operations | 2 | 2 |  |  |  | 
Humanitarian access and aid worker security |  | 3 |  | 1 | 1 | 
The protection context | 2 | 2 |  |  | 1 | 
Strategy and joint planning |  | 2 | 3 | 2 | 1 | 3
Transitional planning | 1 | 1 |  | 3 |  | 
L3 and related organisational issues |  | ? | 2 | 2 | 1 | 3
Leadership | 2 | 3 | 3 | 2 | 1 | 3
Coordination & collaboration | 2 | 3 | 3 | 2 | 2 | 3
Working with govts |  |  | 3 |  |  | 
Funding (& under-funding) |  |  | 1 | 1 |  | 2
Extract from Evidence Strength Matrix

## Slide 6: Synthesis of thematic findings
1. Context-related findings
2. Strategy & planning, coordination and leadership
3. Programme delivery, effectiveness, coverage, quality
4. Protection, vulnerability, advocacy & humanitarian principles
5. Targeting, accountability and community engagement
6. Staffing, partnerships and operational efficiency
7. Assessment, monitoring and evaluation

## Slide 7: 1: Context-related findings
Deliberately restricted humanitarian space in Syria – variable space in refugee-hosting countries
Lack of effective humanitarian access (even post 2014 UNSC Resolutions) has been the critical limiting factor on aid coverage inside Syria
Protection context: direct targeting of civilians and civil objects in Syria => disregard by all side of basic IHL norms. Temporary or de facto protection in refugee hosting countries, undermined by assistance / livelihood deficits
Evaluation question: What counts as a ‘context finding’?

## Slide 8: 2: Strategy & planning, coordination, leadership
Many reports note lack of overarching strategy
Some evident system ‘disconnects’ (see gap analysis)
CRSF did not get traction. WoS approach seems to have been more effective, though work in progress
Coordination analysis dominated by confusion over respective roles of UNHCR and OCHA/HC; and some overlap between e.g. UNHCR and UNICEF
Coordination now reported improved in most respects
  Evaluation question: To what extent can joint strategy, coordination and other ‘system’ issues be judged from single agency evaluations?

## Slide 9: 3: Programme delivery, effectiveness, coverage & quality
Preparedness: little evaluated, and mainly by process (e.g. contingency planning) rather than actual utility. Organisational flexibility a better measure?
Effectiveness assessed largely by delivery of outputs
Generally positive reports on delivery against immediate objectives – but lack of clarity on (shifting) targets and baselines. NB complication of major funding deficits.
Timeliness: agencies slow to wake up to scale of crisis
Coverage: major gaps inside Syria, fewer outside
Quality: little evaluation against standards

## Slide 10: 4: Protection, vulnerability, advocacy & humanitarian principles
Despite the SG’s HRs Up Front initiative, UN protection efforts in Syria not well joined up
Too much by way of ‘normative statements’, too little by way of ‘actionable commitments’
Limited incentive for HC/HCT to take bold decisions?
Refugee protection relatively successful, given lack of strong international legal frameworks
Weak analysis of advocacy (strategy, coherence, effectiveness)
Weak evaluation against humanitarian principles, though questions about independence raised by some in regard to relationship of UN agencies with governments.
Evaluation question: How should protection and advocacy responses be evaluated in a context like this? And principles?

## Slide 11: 5: Targeting, accountability & community engagement
Limitations of accountability in Syria acknowledged but scope for more to be done
Lessons from limited initial community engagement in Zaatari camp – and subsequent social mobilisation
Work on social cohesion needs to be better joined up
Major challenges to working effectively with refugees in host communities (and little reliable data)
Questions about shared or segregated services for refugees and host communities
Evaluation question: how should accountability be evaluated?

## Slide 12: 6: Staffing, partnerships & operational efficiency
Many report staffing problems associated with organisational overstretch: short term deployments, high turnover, multiple surge deployments (UN).
=> discontinuity, inefficiency
Lessons from regional management structures & processes
Inflexibility in budget-based financial management?
Efficiency proved hard to evaluate given available data and lack of clear comparators
Partnerships very little analysed in terms of their effectiveness or appropriateness
Evaluation question: why is efficiency so weakly evaluated? What about the evaluation of partnerships/ deliver chains? How do transaction costs feature in cost-benefit analysis?

## Slide 13: 7: Assessment, monitoring & evaluation
Weakness of assessment inside Syria. Largely down to access and security constraints, but not entirely.
Learning from the J-RANS, SINA, MSNA, HNO processes
Large amounts of assistance are being delivered inside Syria ‘with very light independent monitoring based on incomplete or non-existent assessment analysis’ . Accountability issues…
Situation better in refugee hosting countries, tho’ even here ‘a striking absence of… data and information about the situation of refugees living in host communities’ (UNICEF Turkey)
Weak evaluation of monitoring and information management
Evaluation question: how to evaluate (i) the quality of needs analysis; (ii) the extent to which decisions are evidence-based?

## Slide 14: Gap analysis

## Slide 15: Most significant evaluation gaps?
Analysis of the humanitarian response inside Syria – including coverage, relevance, effectiveness, accountability and financial management
‘Do no harm’ principle, impartiality & related aspects of risk management
Funding shortfall implications & analysis of unmet needs.
System analysis and disconnects: UN and INGO

## Slide 16: Significant evidence gaps (1)
Financial management + finance and funding mechanisms
Organisational capacity and overstretch
Quality of aid / compliance with standards
Remote assistance, remote management
Transition planning, ‘resilience’ programming
Humanitarian principles: application and compliance

## Slide 17: Significant evidence gaps (2)
Preparedness and organisational readiness
Advocacy and influencing strategies
Situation and treatment of minorities
Refugees in host communities + urban assistance
Gender, age and vulnerability
Monitoring, reporting and information management
Staff and partner security + risk management

## Slide 18: Overall conclusions (1)
While not possible to draw firm overall conclusions about the overall international humanitarian response to the Syrian crisis, some indicative conclusions can be drawn – as illustrated above.
The available evaluative material is less comprehensive than one might expect after 4 years+ of responses. What else is out there? What is planned?
Lack of system-wide analysis, but some observations possible. While some aspects of the system have evidently worked well, it was highly compromised inside Syria, sometimes slow to respond elsewhere, and somewhat hampered by confusion over leadership. Undermined by weak or late international political engagement, and massively affected by chronic underfunding.

## Slide 19: Issues arising (1) – System-related
The relationship (synergy / tensions) between the political and humanitarian components of the international response
The financing of protracted responses, including agency advance financing capacities and strategic coordination between donor governments.
‘System’ coherence and efficiency, including the respective coordination and leadership roles of different UN agencies, particularly in refugee contexts; the added value and relative efficiency of partnership arrangements (particularly UN-INGO-LNGO); system capacity and its limits.
The respective and joint roles of humanitarian and development actors in protracted crises (resilience etc.); including the ways in which they engage with host governments over time.

## Slide 20: Issues arising (2) – programming and operational
Cross-border programming & remote partnership management
Assisting and protecting people in urban settings – and the related topic of assisting dispersed refugee populations
Working with refugees and host communities – programming for social cohesion.
Resilience programming, particularly livelihood support in restrictive environments. Policy and programming aspects.
Sector-specific learning. There is a considerable body of learning here, notably on the use of cash and vouchers, which merits consolidation and wider dissemination.